 Timeline

November

    Nov 1 Choose a date and a site
    Nov 1 Program Chair named

December

January

February

March

    Mar 15 Basic website created
    Mar 15 First draft budget created
    Mar 23 Website live with venue, hotel, Friends, prospectus
    Mar 28 F2F meeting at ECon
    Mar 29 ECE 2012 announced at ECon 2012

April

    Apr 10 Sponsor prospectus and agreement finalized
    Apr 10 Sponsor booth map done
    Apr 10 Friends logos/banners on website
    Apr 13 Add PC names to mailing list and create ECon wiki accounts
    Apr 13 Website ready: front page, sponsor prospectus, etc.
    Apr 15 Program Committee named
    Apr 16-24 Email to alumni sponsors "Here's the prospectus and map; sign up now for the best choice
    Apr 24 Conference format chosen - track categories, talk types, etc.

May

    May 1 Submission system working
    May 7 Let DemoCamp organizers know that we will have handouts for them to distribute
    May 7 Copy to printer for DemoCamp promo
    May 7 Submission/Speaker FAQs on website
    May 8 Website: "Plan to Participate"
    May 8 Submissions open at T-24 weeks
    May 8 Marketing message: "CFP" (community bulletin, forums, mailing lists, social networking sites)
    May 8 Email to alums: "CFP"
    May 11 Draft budget submitted
    May 15 Budget to Finance Committee
    May 15 Hotel block reserved
    May 16 Submit translated contract to CFO
    May 17 DemoCamp ECE promo ready
    May 23 Send promo handout to DemoCamp organizers

June

    Jun 1 Hotel, venue, etc. information on website
    Jun 4 Return signed contract to Venue
    Jun 14 Email to sponsors via members/committers email list
    Jun 15 Registration FAQs page ready for review
    Jun 15 Keynote agreement template done
    Jun 15 Reg survey questions
    Jun 29 Early Bird sponsor deadline

July

    Jul 2 Keynotes chosen
    Jul 3 Website: Great Keynotes
    Jul 3 Marketing message: "Keynotes announced, CFP reminder" to alums, members-committers, eclipse-announce, Facebook, Twitter
    Jul 6 Copy to Printer for keynote promo
    Jul 11 Marketing message "CFP Early-bird Reminder" on eclipse.org, to members-committers list, eclipse-announce list, Twitter, Facebook, LinkedIn, etc
    Jul 11 Marketing message "CFP Early-bird Reminder" email to alums
    Jul 11 Website: Send your early-bird submissions now
    Jul 13 Keynote promo ready
    Jul 13 Accept/decline email text finalized
    Jul 13 Speaker agreement text finalized
    Jul 15 Early-bird submission deadline
    Jul 16 Pre-opening reg page ready
    Jul 23 Early-bird submitters notified
    Jul 24 Website: "Early-bird selections"
    Jul 24 Remind everyone to blog about contest winners and submissions deadline
    Jul 24 Remind PC to start blogging about early-bird contest
    Jul 24 Website: Final Call for Papers
    Jul 24 Marketing message "Final Reminder for Call for Papers" eclipse.org news, members-committers, announce, forums, Twitter, Facebook, LinkedIn, etc.
    Jul 25 Email to alums: "Final CFP"
    Jul 30 Website: Registration opening soon
    Jul 31 Submissions close at T-12 weeks

August

    Aug 1 Registration opens
    Aug 7 Website: Registration Is Open
    Aug 7 Marketing message: "Registration is open" Facebook
    Aug 8 Reminder to sponsors about workshop submission deadline
    Aug 15 Deadline for sponsored workshop submissions
    Aug 15 Speaker coupon codes created
    Aug 15 Speaker Agreement finalized
    Aug 20 Sponsor Email 2 to sponsors
    Aug 21 Program finalized at T-9 weeks
    Aug 23 Accept/decline emails sent
    Aug 28 Program on website at T-9 weeks
    Aug 29 Add ECE banner to eclipse.org home page
    Aug 29 Schedule sponsored workshops
    Aug 29 Let sponsors know their workshops are scheduled
    Aug 30 First Emailed Newsletter "Program ready; great keynotes; register now" to alums, members-committers, forums, social media
    Aug 30 Email to speakers: "you are responsible for your website content"
    Aug 31 Revisit booth map re possible adjustments

September

    Sep 1 Deadline for selling lanyard sponsor
    Sep 1 Deadline for sponsor logos and company descriptions for printed program
    Sep 5 email current registrants and remind them to go back in and pre-register for tutorials
    Sep 7 Arrange for blocks with other hotels
    Sep 10 Nestor hotel block cutoff
    Sep 10 Update Hotels page with other options
    Sep 10 Deadline for sponsor ads in program
    Sep 13 Schedule IWG meetings
    Sep 17 Printed program content due: keynotes, Welcome letter, special events, track descriptions
    Sep 17 Reminder pay Venue by Oct. 15
    Sep 17 Deadline for ordering lanyards
    Sep 17 Deadline for speakers to have content corrected for printed program
    Sep 18 Second emailed newsletter - focus on activities, program; to alums, members-committers, social media
    Sep 19 Printed program data pull done
    Sep 20 Create attendee survey draft
    Sep 20 Set up submission system for BoFs
    Sep 21 Banner layout done
    Sep 24 Open BoF submissions
    Sep 24 Website: submit a Bof
    Sep 25 Third emailed newsletter - register before early deadline, submit a BoF" to alums, members-committers, social media
    Sep 27 Write post-conf email "Thanks for attending and take the survey"
    Sep 28 Printed program: first draft ready
    Sep 30 Last day for Early registration
    Sep 30 Send post-conference email

October

    Oct 1 Request Venue invoice payment
    Oct 1 Printed program: final draft approved
    Oct 10 Pay printer deposit
    Oct 8 Program goes to printer
    Oct 9 Fourth emailed newsletter - "Three weeks until ECE" to alums, members-committers, social media
    Oct 10 Finalize attendee survey
    Oct 10 Print BoF and other hard copy stuff
    Oct 15 Website future home pages, including Flickr stuff
    Oct 15 Deadline for advance registration
    Oct 15 Finalize "Welcome to ECE" email
    Oct ? Venue payment due
    Oct 18 "Welcome to ECE" email to registrants
    Oct 19 Last day for advance registration
    Oct 23 Conference Is Happening
    Oct 26 Website: Thanks for attending; take the survey
    Oct 30 email to attendees: "Thanks, please take our survey"