FOOS4G 2009 Program Timeline

17 – 21 November 2009

OC = Organising Committee

TH = Tour Hosts

| Date | Activity | Action |
| --- | --- | --- |
| 30 May 2008 | Discussion on requirements for abstract submission form/program: Presentation types: Oral and/ or Poster? Conference themes Author information required: Biographies? Can authors submit more than one abstract? Are session chairs or Keynote abstracts required Reviewers – Are session chairs to review all abstracts submitted under their session theme? Abstracts only or abstracts and full papers? | OC/TH |
| November 2008 | Invite keynote speakers. | OC/TH |
| November 2008 | Confirm guidelines for submission of abstracts | TH/OC |
| November 2008 | Call for Abstracts, workshops and lab proposals draft text to be developed and confirmed by the OC. | TH/OC |
| November 2008 | List of potential abstract reviewers/referees confirmed. | OC |
| December 2008 | Online abstract, workshops and lab proposals submission form setup and ready for testing. | TH |
| January 2009 | Call for abstracts, workshops and lab proposals form activated on website. Email blast distributed promoting call for abstracts, workshops and lab proposals open. | TH/OC |
| February 2009 | Discussion regarding criteria for review of abstracts Including: Scoring Acceptance/Rejection Reviewer Access | TH/OC |
| May 2009 | TH to process abstracts available for review. OC to review themes for each abstract ensuring they have been submitted under the correct theme. | TH/OC |
| May 2009 | Reviewer Zone set up and ready for testing. | TH/OC |
| May 2009 | Access to Reviewer Zone and instruction given to reviewers to review/score abstracts online. | TH |
| 27 May 2009 | Closing date for abstract, workshop and lab submissions. | TH |
| 17 June 2009 | Completion of abstract review process. |  |
| June - July 2009 | OC to allocate abstracts into the program. | OC |
| June - July 2009 | Confirm session chairpersons and room allocation. | OC |
| 13 July 2009 | Final program confirmed and sent to TH. | OC |
| July 2009 | TH to enter program into database. | TH |
| July 2009 | All letters to be drafted for authors: Oral acceptance letter Poster acceptance letter Rejection letter Oral presentation guidelines Poster presentation guidelines Invited speaker – confirmation of presentation times/ dates/ program information. OC to review and confirm letters. TH to set up letters in the database. | TH/OC |
| 27 July 2009 | Abstract acceptance notification | TH |
| 12 August 2009 | Author/ Early Bird Registration Deadline | TH |
| August 2009 | Chase outstanding speaker registrations. List of unregistered authors to OC for review of program order. | TH OC |
| November 2009 | Conference commences |  |