## FOSS4G 2009 Program Timeline

## 21 – 23 October 2009

OC = Organising Committee / TH = Tour Hosts

| DATE | ACTIVITY | ACTION | COMMENTS |
| --- | --- | --- | --- |
| Dec 2008 / January 2009 | Discussion on requirements for workshop/lab submission process: OC to discuss format of workshops Total number of workshops to be accepted (ie: 5 rooms at SCEC therefore 10 half day workshops) OC to set up ‘call’ email and template of workshop submission form | OC/TH |  |
| January-February 2009 | Discussion on requirements for abstract submission process: OC to discuss presentation type (oral and poster) Select categories (ie: software/ technical/ business/ case study) Author biography required Word Limit OC to set up ‘call’ email and template of submission form | OC/TH |  |
| 2 February 2009 | Call for Workshops/Labs open online | OC |  |
| Early Feb 2009 | Discuss registration form and requirements with OC TH to draft necessary registration text to place on website including accommodation/social functions/ registration types/workshop registration fees/cancellation policy etc. | OC/TH |  |
| 2 March 2009 | Call for Workshops/Labs submission deadline | OC | In 2007 – 52 workshop proposals received |
| 9 March 2009 | Call for abstracts open online | OC |  |
| March 2009 | Registration online form set up and ready for testing OC to complete ‘dummy’ registration to ensure happy with online process | TH |  |
| 30 March 2009 | Notification of Acceptance for Workshops Workshop session information available on website/wiki | OC |  |
| Early April 2009 | Website updated with registration information | OC/TH |  |
| 13 April 2009 | Registration for Conference and Workshops opens online | OC/TH |  |
| Early May 2009 | Discussion regarding criteria for review of abstracts including; Scoring/ranking process OC to be aware that once the community has ranked the Committee will need to select the final talks for presentation | OC |  |
| May 2009 | OC to formulate list of chairpersons for each session | OC |  |
| 15 June 2009 | Abstract submission deadline | OC | In 2007 – 213 received: (73 on last day, 39 on second last day and 13 on third last day) |
| June 2009 | TH to draft guidelines for presenters to be sent with acceptance emails on 13 July. | TH |  |
| 16 June – 30 June 2009 | All abstracts ranked by community | OC |  |
| 1 July – 8 July 2009 | Committee to use ranking numbers to select final presentations for sessions. OC to create acceptance email for accepted presenters. | OC |  |
| 13 July 2009 | Presenters notified of acceptance for talks | OC | In 2007 scheduled 120 talks with 10 additionals as stand by. Each talk 20 mins each incl Q&A. |
| 31 July 2009 | Author/Early Registration Deadline |  |  |
| Mid August 2009 | Chase outstanding presenter registrations Send list of unregistered authors to OC for review of program order | OC/TH |  |
| 14 September 2009 | Complete program of sessions available on website/wiki | OC |  |
| Mid September 2009 | Draft chair briefing notes and send to OC for approval Distribute chair briefing notes | OC/TH |  |