## 2014
FOSS4G Annual Meeting - September 8-14, 2014 | Due Date | Days remaining | Status | Owner | Notes
Countdown to Event | 2014-09-08 | 308
Budget
Complete transfer of seed money | 2013-11-08 | 4 |  | OSGeo
Update event budget | 2013-11-08 | 4 |  | VTM
Web site
Request graphics | 2013-11-08 | 4 |  | LOC
Update web site with graphics, general event info | 2013-11-29 | 25 |  | LOC
Update web site with sponsor info | 2013-11-29 | 25 |  | LOC
Website able to accept proposals | 2013-12-15 | 41 |  | LOC
Update web site with agenda | 2014-06-02 | 210 |  | LOC
Vendors
Secure hotel contract | 2013-11-18 | 14 |  | VTM
Secure sleeping hotel (Doubletree) | 2013-11-18 | 14 |  | VTM
Secure Graphic designer | 2013-11-18 | 14 |  | VTM
Secure e3 Webcasting | 2013-11-18 | 14 |  | VTM
Secure Eliot center | 2013-11-18 | 14 |  | VTM
offsite venues for receptions/dinners | 2013-12-09 | 35 |  | VTM
offsite pub night(s) | 2014-03-01 | 117 |  | LOC/VTM
Venue
Oregon Convention Center (OCC)
Initial floor plan discussion | 2013-12-16 | 42 |  | LOC/VTM
Request security proposal from CVB | 2014-02-03 | 91 |  | VTM
F&B | 2014-08-01 | 270 |  | VTM
Audio Visual Needs | 2014-08-01 | 270 |  | VTM
Submit floor layouts to OCC for fire Marshall approval | 2014-08-05 | 274 | **confirm in contract | VTM
Confirm internet access details for attendees | 2014-08-08 | 277 |  | VTM
No. of seats for lunch | 2014-08-25 | 294 |  | VTM
Eliot Center
Initial floor plan discussion | 2014-02-03 | 91 |  | LOC/VTM
F&B | 2014-08-01 | 270 |  | VTM
Audio Visual Needs | 2014-08-01 | 270 |  | VTM
Submit floor layouts for fire Marshall approval | 2014-08-05 | 274 |  | VTM
Confirm internet access details for attendees | 2014-08-08 | 277 |  | VTM
No. of seats for lunch | 2014-08-25 | 294 |  | VTM
Sponsors
Update sponsor options | 2013-11-29 | 25 |  | LOC
Email sponsors that reg is open | 2013-12-02 | 28 |  | LOC
First draft of Exhibitor Handbook due | 2013-12-05 | 31 |  | VTM
early bird sponsor deadline | 2013-12-31 | 57
Open sponsor registration to members | 2014-01-01 | 58
Final draft of Exhibitor Handbook due | 2014-01-07 | 64 |  | VTM
Distribute Exhibit Handbook | 2014-01-08 | 65 |  | LOC
Collateral Reminder Email to Sponsors | 2014-05-30 | 207 |  | LOC
Last day to accept exhibiting sponsors | 2014-06-16 | 224
Sponsors select booth space
Collateral due | 2014-06-30 | 238
Finalize exhibit floor plan | 2014-06-30 | 238 |  | LOC/VTM
Sponsor payments due | 2014-07-01 | 239 |  | VTM
Speakers
Create timeline | 2013-11-15 | 11 |  | LOC
Draft "Call for Papers" | 2013-12-16 | 42 |  | LOC
Create "Call for Papers" web page | 2013-12-16 | 42 |  | LOC
Issue "Call for Papers" | 2014-01-01 | 58 |  | LOC
Academic abstract submission deadline | 2014-02-01 | 89 |  | LOC
Brainstorm speaker "Thank you" gifts | 2014-02-03 | 91 |  | LOC/VTM
Close "Call for Papers" | 2014-03-03 | 119 |  | LOC
All draft presentations due | 2014-03-05 | 121
Speaker/staff shirts | 2014-04-01 | 148 |  | VTM
Regular Track presentation deadline | 2014-04-15 | 162 |  | LOC
Open community on presentations | 2014-04-16 | 163 |  | LOC
Finalize speaker "Thank you" gifts | 2014-05-01 | 178 |  | VTM
Close community comments on presentations | 2014-05-01 | 178 |  | LOC
Final presentations for review | 2014-06-02 | 210 |  | LOC
Signed speaker agreements due | 2014-06-30 | 238 |  | VTM
Post presentations for members-only download
Speaker travel coordination (lodging/airfare) | 2014-07-01 | 239 |  | VTM
Confirm speaker clocks for tracks |  |  |  | VTM
Registration
Create sponsor/speaker/attendee registration pathways | 2013-11-25 | 21 |  | VTM
Open Early bird sponsor registration | 2013-12-02 | 28 |  | VTM
Early Bird Sponsorship closes | 2013-12-31 | 57 |  | VTM
Open regular sponsor registration | 2014-01-01 | 58 |  | VTM
Open speaker registration | 2014-01-01 | 58 |  | VTM
Open early bird attendee registration | 2014-03-01 | 117 |  | VTM
early bird workshop registration opens | 2014-03-03 | 119 |  | VTM
speaker registration closes | 2014-06-02 | 210 |  | VTM
Early Bird attendee Registration Discount Ends | 2014-06-15 | 223 |  | VTM
Regular sponsor registration closes | 2014-06-16 | 224 |  | VTM
regular attendee registration opens | 2014-06-16 | 224 |  | VTM
regular workshop registration opens | 2014-06-16 | 224 |  | VTM
Create on-site attendee registration pathway | 2014-08-01 | 270 |  | VTM
regular attendee registration ends | 2014-09-03 | 303 |  | VTM
Agenda
Draft agenda | 2014-06-15 | 223 |  | LOC/VTM
Finalize event agenda | 2014-08-22 | 291 |  | LOC/VTM
Post final agenda | 2014-08-25 | 294 |  | LOC/VTM
Email final agenda to vendors | 2014-08-25 | 294 |  | LOC
Advertising
Web page updated | 2013-11-18 | 14 |  | LOC
1st email blast - "Save the Date! / Early Bird Sponsor Reg is Open" | 2013-12-02 | 28 |  | LOC/VTM
Blast - "Early bird Sponsor Registration Reminder" | 2013-12-16 | 42 |  | LOC/VTM
Blast - "regular sponsor registration is open" | 2014-01-01 | 58 |  | LOC/VTM
Blast - "Early Bird Registration is Open" | 2014-03-03 | 119 |  | LOC/VTM
Blast reminder - "Registration reminder" | 2014-03-17 | 133 |  | LOC/VTM
Blast reminder - "Registration reminder" | 2014-04-14 | 161 |  | LOC/VTM
Blast reminder - "Registration reminder" | 2014-05-14 | 191 |  | LOC/VTM
Blast - Early bird registration is closing reminder | 2014-06-02 | 210 |  | LOC/VTM
Blast reminder - "Regular Registration is open reminder" | 2014-06-16 | 224 |  | LOC/VTM
Blast reminder - "Registration Reminder" | 2014-07-14 | 252 |  | LOC/VTM
Blast "One Month Left to Register" | 2014-08-01 | 270 |  | LOC/VTM
Blast "Don't Forget to Register" | 2014-08-08 | 277 |  | LOC/VTM
Blast - "Two Weeks Left to Register" | 2014-08-15 | 284 |  | LOC/VTM
Blast - "One Week Left to Register" | 2014-08-22 | 291 |  | LOC/VTM
Blast - "Last Chance to Register" | 2014-08-27 | 296 |  | LOC/VTM
Registration closes at 5pm (PT) | 2014-08-29 | 298 |  | VTM
Name badges sent to printer | 2014-09-01 | 301 |  | VTM
Ticket to printer | 2014-09-01 | 301 |  | VTM
Registration reports |  |  |  | VTM
Graphics
Discuss sign and banner needs | 2014-03-03 | 119 |  | LOC/VTM
pricing quotes | 2014-06-02 | 210 |  | VTM
Finalize sign and banner needs | 2014-07-01 | 239 |  | LOC/VTM
Programs | 2014-07-01 | 239 |  | LOC/VTM
Sign and banner content to vendor | 2014-07-01 | 239 |  | VTM
Design name badges/tickets | 2014-07-15 | 253 |  | VTM
Banners/signage to VTM for review | 2014-08-01 | 270 |  | VTM
Approve all material for print | 2014-08-01 | 270 |  | VTM
Name badge/ticket proofs | 2014-08-01 | 270 |  | VTM
Materials sent to print | 2014-08-18 | 287 |  | VTM
On-site print inspection | 2014-08-25 | 294 |  | VTM
e3 Webcasting
Complete contract | 2013-12-30 | 56 |  | VTM
Schedule kick-off with e3 | 2014-05-01 | 178 |  | LOC/VTM
Surveys
Discuss raffle survey prizes
Finalize raffle survey prizes
Create attendee survey | 2014-06-30 | 238
Create sponsor survey | 2014-06-30 | 238
Attendee survey to print | 2014-08-15 | 284
Sponsor survey to print | 2014-08-15 | 284
Other
book any transpiration needed (reception/offsites) | 2014-04-01 | 148 |  | VTM
Select Attendee Swag bags | 2014-05-01 | 178 |  | LOC/VTM
Select Attendee Swag t-shirts | 2014-05-01 | 178 |  | LOC/VTM
Discuss "Other" Swag bag content | 2014-05-01 | 178 |  | LOC/VTM
Order all Swag bag items | 2014-06-01 | 209 |  | VTM
Confirm when insurance rider due to OCC & offsite reception venue |  |  |  | VTM
Request insurance rider |  |  |  | VTM
Insurance to OCC | 2014-08-08 | 277 |  | VTM
OCC reader-board text | 2014-08-08 | 277 |  | VTM
Rooming list to hotel | 2014-08-08 | 277 |  | VTM
Attendee packets (to include travel pdx maps, dinner options etc.) | 2014-08-08 | 277 |  | VTM
Draft POE | 2014-08-08 | 277 |  | VTM
Arrange for office to be re-keyed | 2014-08-08 | 277 |  | VTM
Walk thru | 2014-08-27 | 296 |  | VTM
Finalize POE | 2014-08-29 | 298 |  | VTM
Workshop @ PSU
Call for Workshops | 2014-03-31 | 147
Draft schedule of events | 2014-05-01 | 178 |  | LOC/VTM
work with venue on F&B/AV needs | 2014-08-04 | 273 |  | VTM
Hackathon
Draft schedule of events | 2014-05-01 | 178 |  | LOC/VTM
work with venue on F&B/AV needs | 2014-08-04 | 273 |  | VTM
Post Event
Post mortem | 2014-09-16 | 316 |  | LOC/VTM
Survey entry | 2014-09-22 | 322 |  | VTM
Sponsor roll-up presentation and distribution | 2014-09-22 | 322 |  | VTM
Speaker follow-up | 2014-09-22 | 322 |  | LOC
Formulas:
Days remaining = [Due Date]-TODAY()